## Defect Log
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Diya Wani | 19/12/2025 | Retrieved document chunks were not always relevant for certain user queries | Sprint 2 | Self | Logical | Improved retrieval mechanism by optimizing chunk size and similarity search parameters | 2026-02-20 | Closed | Retrieval relevance improved significantly
2 | Diya Wani | 22/12/2025 | Generated answers did not include proper source citations for some responses | Sprint 3 | Self | Standards | Modified prompt to enforce source citation and updated response formatting logic | 2026-02-23 | Closed | Citation issue resolved
3 | Diya Wani | 26/12/2025 | Chat UI was not updating after new messages were added | Sprint 3 | Self | Functional | Replaced list append with new list assignment to ensure reactivity | 2026-02-27 | Closed | UI updates working correctly
4 | Diya Wani | 29/12/2025 | Uploaded documents were not being processed for multiple file uploads | Sprint 2 | Self | Functional | Enabled multiple file handling and updated upload logic | 2026-03-03 | Closed | Multiple file upload supported
5 | Diya Wani | 02/01/2026 | System failed when documents folder was not present | Sprint 1 | Self | Runtime | Added dynamic folder creation before file storage | 2026-03-05 | Closed | Error handling improved
6 | Diya Wani | 04/01/2026 | Slow response time for large documents during query processing | Sprint 4 | Self | Performance | Optimized chunk size and reduced number of retrieved documents | 2026-03-06 | Closed | Response time improved
7 | Diya Wani | 06/01/2026 | Conversation history was not being considered in follow-up queries | Sprint 3 | Self | Logical | Injected chat history into prompt for better context handling | 2026-03-07 | Closed | Follow-up questions handled correctly
8 | Diya Wani | 08/01/2026 | Irrelevant answers generated when retriever failed | Sprint 4 | Self | Logical | Implemented corrective RAG with relevance check and query rewriting | 2026-03-09 | Closed | Answer accuracy improved
9 | Diya Wani | 10/01/2026 | Application crashed when unsupported file formats were uploaded | Sprint 2 | Self | Runtime | Added file type validation and error handling | 2026-03-11 | Closed | System stability improved
10 | Diya Wani | 12/01/2026 | Chat history page did not display sources properly | Sprint 3 | Self | UI | Updated rendering logic for sources in history page | 2026-03-13 | Closed | Sources displayed correctly
11 | Diya Wani | 14/01/2026 | Duplicate document embeddings created on repeated uploads | Sprint 4 | Self | Logical | Added duplicate check before inserting into vector store | 2026-03-15 | Closed | Duplicate entries avoided
12 | Diya Wani | 16/01/2026 | High memory usage due to persistent vector storage | Sprint 4 | Self | Performance | Removed persistent storage and switched to session-based vectorstore | 2026-03-17 | Closed | Memory usage reduced
13 | Diya Wani | 18/01/2026 | UI layout issues on smaller screens | Sprint 3 | Self | UI | Improved responsive design using flexible layouts | 2026-03-19 | Closed | UI responsiveness improved
14 | Diya Wani | 20/01/2026 | No loading indicator during document processing | Sprint 2 | Self | UI | Added loading spinner for better user feedback | 2026-03-21 | Closed | User experience improved
15 | Diya Wani | 22/01/2026 | Authentication not implemented for multi-user access | Sprint 4 | Self | Security | Planned authentication module (not yet implemented) |  | Open | To be implemented in future scope