## User Stories
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload documents so that they can be searched | MUST HAVE | None | Diya Wani | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a user, I want semantic search over documents | MUST HAVE | US-01 | Diya Wani | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a user, I want conversational Q&A | MUST HAVE | US-02 | Diya Wani | 3- Completed
Sprint 4 | Sprint 4 | US-04 | As a user, I want source citations in answers | SHOULD HAVE | US-03 | Diya Wani | 3- Completed
Sprint 5 | Sprint 5 | US-05 | As a user, I want follow-up question handling | SHOULD HAVE | US-04 | Diya Wani | 3- Completed
Sprint 6 | Sprint 6 | US-06 | As a user, I want chat history tracking | COULD HAVE | US-03 | Diya Wani | 3- Completed
Sprint 7 | Sprint 7 | US-07 | As a user, I want improved retrieval accuracy using corrective RAG | SHOULD HAVE | US-02 | Diya Wani | 3- Completed
Sprint 8 | Sprint 8 | US-08 | As a user, I want session-based memory for temporary document handling | COULD HAVE | US-01 | Diya Wani | 3- Completed
Sprint 9 | Sprint 9 | US-09 | As a user, I want a responsive UI for better usability | COULD HAVE | None | Diya Wani | 3- Completed
Sprint 10 | Sprint 10 | US-10 | As a user, I want authentication for secure access | WON’T HAVE | None | Diya Wani | 1- Pending